## Tasks
Task Name | Sub Tasks | Duration | Start Date | End Date | Ignore this column - Rough
CMU Rental Hub Project |  | 70 Days | 2025-01-22 | 2025-04-28
Project Proposal & Idea Finalization |  | 4 Days | 2025-01-22 | 2025-01-27
1 | Brainstorm project ideas & shortlist top 3 | 2 Days | 2025-01-22 | 2025-01-23
2 | Discuss ideas with professor and get feedback | 1 Day | 2025-01-24 | 2025-01-24 | 25, 26
3 | Finalize project based on feedback & document proposal | 1 Day | 2025-01-27 | 2025-01-27 | 27- Project Proposal
Project Planning & Initial Designs |  | 15 Days | 2025-01-28 | 2025-02-17
4 | Create Draft ERD | 7 Days | 2025-01-28 | 2025-02-05 | 1,2
5 | Create Draft Context-Level & Level-0 DFD | 6 Days | 2025-02-06 | 2025-02-13 | 8,9
6 | Prepare Task List | 1 Day | 2025-02-14 | 2025-02-14 | 15,16
7 | Develop Critical Path | 1 Day | 2025-02-17 | 2025-02-17 | 2/17 - project plan
Revisions Based on Feedback |  | 10 Days | 2025-02-18 | 2025-02-28
8 | Update and finalize DFD | 4 days | 2025-02-18 | 2025-02-21 | 22,23
9 | Review professor's suggestions & update ERD | 5 Days | 2025-02-24 | 2025-02-28 | feb 24 dfd, march 3 erd
Database Development (MySQL) |  | 10 Days | 2025-03-03 | 2025-03-14
10 | Design database schema in MySQL | 4 Days | 2025-03-03 | 2025-03-06
11 | Create tables and relationships | 2 Days | 2025-03-07 | 2025-03-10 | 8,9, 15, 16
12 | Implement SQL script | 4 Days | 2025-03-11 | 2025-03-14 | SQL scripts- march 17
Business Logic & Backend Implementation (Python) |  | 8 Days | 2025-03-17 | 2025-03-26
13 | Define technical and functional requirements for backend system | 4 days | 2025-03-17 | 2025-03-20 | 22,23
14 | Implement core business logic using Python | 4 Days | 2025-03-21 | 2025-03-26
User Interface Implementation (Tkinter) |  | 8 Days | 2025-03-27 | 2025-04-07 | 29,30
15 | Design UI & layout | 4 Days | 2025-03-27 | 2025-04-01 | 5,6
16 | Implement Tkinter UI and integrate with backend | 4 Days | 2025-04-02 | 2025-04-07 | April, 7 - UI
Testing & Debugging |  | 7 Days | 2025-04-08 | 2025-04-16
17 | Manual Integration testing | 3 Days | 2025-04-08 | 2025-04-10
18 | Fix errors and optimize performance | 4 Days | 2025-04-11 | 2025-04-16 | 12,13
Project Presentation & Documentation |  | 8 Days | 2025-04-17 | 2025-04-28
19 | Complete final documentation | 3 Days | 2025-04-17 | 2025-04-21 | 19,20
20 | Prepare final project presentation | 1 Day | 2025-04-22 | 2025-04-22
21 | Final project presentation | 3 Days | 2025-04-23 | 2025-04-25 | 26,27
22 | Submit project and wrap up | 1 Day | 2025-04-28 | 2025-04-28